## Sheet1
功能模块 | 说明 | 平台开发状态 |  | 页面样例
|  | Android | IOS | Android |  |  | IOS
跨平台核心功能 |  |  |  | 测试机 | MeiZu | note2 |  | Iphone Retina 3.5'
基础平台 |  | 完成 | 完成
界面描述文件解析 | XML格式，借用HTML标签描述，以减少学习时间 | 完成 | 完成 | 分辨率 | 1080*1920 |  |  | 320*480
界面元素属性解析 | CSS描述样式 | 完成 | 完成
跨平台脚本程序引入和执行 | 脚本可控制界面元素 | 完成 | 完成
原生对象注入到脚本程序环境 | 脚本可调用原生代码 | 完成 | 完成
脚本注入原生环境 | 原生代码可调脚本代码 | 完成 | 完成
网络
支持网络远程调用 | 程序文件和资源文件可安装在网络服务器上。 | 完成 | 未开始
版本自动更新 | 针对本地安装的app | 进行中 | 未开始
网络服务器通讯 |  | 完成 | 未开始
信息推送 |  | 完成 | 未开始
文件下载 | 下载文件到手机内存 | 完成 | 完成
数据功能
文件输入流 |  | 完成 | 完成
随机文件读写 |  | 完成 | 完成
SQLite3数据库 |  | 完成 | 完成
PIM |  | 进行中 | 未开始
界面
界面缓存 |  | 完成 | 进行中
资源自适应
图片、尺寸自适应 | 多种规格屏幕自动适应、计算 | 未开始 | 未开始
自动布局
线性布局 |  | 完成 | 完成
层布局 |  | 完成 | 完成
相对布局 |  | 进行中 | 进行中
流动框 |  | 完成 | 完成
其它更多布局 |  | 未开始 | 未开始
元素
按钮 |  | 完成 | 完成
文本框 | 支持多行文本 | 完成 | 完成
输入框 |  | 完成 | 完成
表格 |  | 完成 | 完成
更多元素 |  | 未开始 | 未开始
多媒体
视频 |  | 完成 | 未开始
音频 |  | 完成 | 未开始
图像展示面板 | 暂时可由带背景的文本框实现 | 进行中 | 进行中
事件
点击事件 |  | 完成 | 完成
手势 |  | 进行中 | 进行中
动画
事件动画 |  | 未开始 | 未开始
翻屏动画 |  | 未开始 | 未开始
其它更多特点 |  | 未开始 | 未开始
更多远期目标
Windows平台支持
自定义界面、功能支持
企业服务总线模式支持
其它网络服务、业务平台支持 | 微信、微博、支付平台等
优化性能
文件上传下载
lfs.c | added

## change list
|  | Android |  |  | IOS
|  | IFileOutputStream.java | Added method | public void writeBoolean(boolean val) | done | remove Android's same name method
|  | Lua updated to V5.1.5 |  |  | is V 5.1.5
|  | added ThreadMethod.java |  | provide thread function | done | IOS不能在lua的initiate函数中自动调用，否则会出错退出，需要手动触发。
|  | StringUtil.java | Added method | public String addParameter(String callback, String param) | done
|  | IFileOutputStream open(String path,String append) |  |  | Did not has this method
|  | IDatePicker.java | added class
|  | Ibutton.java |  | 去除当按下时的背景透明化效果
|  | Iwwdgit.java | added method | getId() | done
|  | AbstractProperties.java | add | lua.regist(Database.class, "Connection"); | done
|  | Icontainer.java | added method | removeAllViews | done
|  | Icamera.java | added class
|  | Main.java |  | onActivityResult--camera callback
|  | Iwedgit.java | modify | public void setBackgroundImageUrl(String backgroundImageUrl); if(backgroundImageUrl.startsWith("file://")) { backgroundImageURL=backgroundImageUrl.substring(7); } else { backgroundImageURL= base + backgroundImageUrl; }
|  | AbstractProperties.java | update | If filebase is not existed, created File fileBaseDir=new File(fileBase); if(!fileBaseDir.exists())fileBaseDir.mkdirs(); | done
|  | ILineChart.java | added class |  | done
|  | BodyView.java | update method | executeLua() remove "connection" of class Database, and move to AbstractProperties.java | done
|  | IFileOutputStream.java | added method | public String readLine()
|  | IFileOutputStream.java | update method | writestring--forced to use UTF-8
| 2016-02-15 | RoundImage.java IRoundImage.java | added class | roung image view | passed
| 2016-02-15 | FileConnector.java | added method | public static String listFiles(String path,String filters)
| 2016-02-18 | AbstractProperties.java | update method | if app server cannot be connected, use local files. boolean isAppServerAccessed=false; if(appServer.startsWith("http://")) { String appJsonUrl=appServer+appBase+"/apps.json"; String appJsonStr=UIFactory.loadOnline(appJsonUrl); if(appJsonStr==null ¦¦appJsonStr.trim().equals("")) { //app server cannot be accessed, do not use it isAppServerAccessed=false; appServer=""; } else { isAppServerAccessed=true; } } if(!isAppServerAccessed ¦¦ isPlatformApp ¦¦ appServer==null ¦¦ appServer=="" ¦¦ !appServer.startsWith("http://")) appBase=sandboxRoot+appBase; else appBase=appServer+"/"+appBase;
| 2016-02-22 | UIFactory.jva | added method | public void switchView(String name) public void switchView(String name,String callback)
| 2016-02-22 | UIFactory.jva | modify | public void switchView(String pageName,String callback,String params,boolean needReload)::: LuaContext.getInstance().doString("exit()"); v.show(); v.execCallBack(callback);
| 2016-02-22 | BodyView.java UIFactory.jva |  | muiltiple line, update how to run Callback function
| 2016-02-29 | UIFactory.jva | added method | cleanViewCache()
| 2016-02-29 | StackX.java | added class
| 2016-02-29 | UIFactory.jva | update method | public void switchView(String pageName,String callback,String params,boolean needReload) this.viewStack.push(name);
| 2016-02-29 | OLAProperties.java |  | protected void onPostExecute(String result) add line: UIFactory.viewStack.push(name);
| 2016-02-29 | OLAProperties.java PortalProperties.java | update method | public void startApp(String appName) add view backup stack
| 2016-02-29 | AppProperties | update method | public void exit()
| 2016-02-29 | Main.java | update method | onKeyDown() updated back actions
notpassed by IOS | 2016-03-01 | Iwedgit.java | update method | parseCSS() update CSS style align and valign's default value to "center" else { p.addRule(RelativeLayout.CENTER_VERTICAL,RelativeLayout.TRUE); }
notpassed by IOS | 2016-03-01 | CSS.java |  | String verticalAlign="middle"; // text position String textAlign="center";
| 2016-03-20 | HTTP.java | update class | added code to process Cookies ,for logon URLs
| 2016-03-20 | Iwedgit.java | update method | setBackgroundImageUrl() added download network URLs
| 2016-03-20 | Iwedgit.java | update method | setBackgroundImageUrl() added to use cookies
| 2016-03-21 | Pim.java | added class
| 2016-05-21 | Iwedgit.java, CSS.java | added Border | 图型背景尚未加上加框 | done
| 2016-05-22 | Iwedgit.java, CSS.java | added font style, font size |  | done
| 2016-05-22 | Ibutton.java,Iwedgit.java,CSS.java | added default CSS
|  | ICheckBox.java | added class
|  | UIFactory.jva | added Password TEXTFIeld Type
|  | Location.java | added class | GPS location
|  | Log.java | added class | logger wrapper | done
|  | AbstractProperties.java |  | 减少网络连接测试时间 AbstractProperties.java 1.move isAppServerAccessed to "public static" 2.change to: if(appServer.startsWith("http://") && isAppServerAccessed) 3.add: else { appServer=""; } UIFactory.loadOnline() add:urlConn.setConnectTimeout(10000);
lua 公用改件改为sandbox/lua下来，修改package.loader注册路径，main中copy lua/目录到手机中
|  | HTTP.java | added getResponse()
|  | IWebView.java | added WebView | ICOntainer.java layout.java
|  | VideoPlayer.java | added class
|  | BaiDUMap.java | added | for Bai Du map
|  | Location.java | updated | for LBS location service
|  | Iwedgit.java | added methods | public void setOnclick(String onclick) { this.onclick=onclick; } public void setPressed(String pressed) { this.pressed=pressed; } public void setReleased(String released) { this.released=released; } | done oc self supported, defined in Iview.h
|  | Session.java | added class | 为了能在app之间存储全局变量
|  | Iwedgit.java | update | 为了减少图片重复率，当图片路径为“$/...”时，取为根路径，否则为app相对路径， public void setBackgroundImageUrl(String backgroundImageUrl,String cookies) else { if(backgroundImageUrl.startsWith("$/")) { bgImageURL= OLA.base + backgroundImageUrl.substring(1); } else { bgImageURL= base + backgroundImageUrl; } }
|  | MethodThread.java | bug
|  | AsyncDownload.java | update | 1.url进行URLEncode 2.callback 函数进行动态组装，允许带有算定义参数 3.自动识别服务器提供 的下载的文件的默认文件名
|  | Database.java | update | added prepared statement methods updare return string: value=value.replace("'", "\\'");
|  | Main.java | update | 启动时copy lua, images目录 | ignored, needn't to copy it
|  | jni/lua/lfs.c | added | added lfs lib to lua, FileConnector will not be used any more
|  | UIFactory.jva | added UI type | else if (name.equalsIgnoreCase("PASSWORD")) { ITextField t= new ITextField(rootView,context,n); t.setInputType(ITextField.TYPE_MASK_FLAGS, ITextField.TYPE_TEXT_VARIATION_WEB_PASSWORD); v=t; }
|  | UIFactory.jva | add method | public String getRootViewId()
|  | IProgressBar.java | updated | muiltiple lines
|  | UIFactory.jva | updated | update method switchView() added code: before load new view, show loading page, after loaded, remove the loading page

## bugs
<div layout="LinearLayout" style="orientation:horizontal;valign:middle;width:auto; align:right;">
align 属性无效，不能使DIV中的元素居中
IOS | assert文件在APP path下面，则程序不能下载更新lua代码,需转移lua文件到Douments下，则可下载更新
database | need to be transered to use Sqlite3.lua

## UI usage
General
| attr | css | values | description | example
id
|  | color |  | hex RGB color | #00FFFFFF;
|  | width |  | px | 100px;
|  | height |  | px
| attr | css | values | description
ProgressBar | type |  | rorate | a rotate(circle) view
|  |  | bar | a horizon bar progress bar
|  |  | circle | a circle progress bar
|  | progress-image |  | image's url

## .xml.Lua structure
the file name should be "*.xml.lua"
life cycle | function initiate() | auto be executed while entered the is view
| function exit() | will be executed while exit this view and switch to an other page
| function swipe(direction) | will a swipe gesture was recognized, the method will be executed
|  | direction | swipe directions, an int value: 1--swipe to right 2--swipre to left | function swipe(direction) if direction==1 then next() elseif direction==2 then previous() end end
| function back() |  |  | function back() ui:switchView("StudyView.xml","reset()","") return 1 end
if returns 0, will exit the app and back to portal, if it is already in portal, exit the software
if returns 1, it is an inner view's back action, do nothing else except the code in this function
default functions
| LMProperties:exit() | in an app, this method while return the app to the portal app
| sys.reload() | reload/refresh the current view, only for Android(mainlyfor Test)
default objects
Log | Log:d(u,m) | u--module name m--messages
Log:i(u,m)
Log:f(u,m)
UI | lui | lui is a encapesulated ui toolkit, see: lua_ui.lua
| createView(viewXml) | create an UI view
xml should has only one root(top) xml node, or will be wrong
viewXml-- the view's description xml string
rerutn--view's id, if the view xml do not has an ID, will auto assigned one
| addView(id) | add a sub view to the current view
| removeView(id) | remove a subview
| switch(viewName, callMethod, params) | forward to another view
|  | viewName | the view's xml file name will be forwarded to
|  | callMethod | called method name while entered the forwarded view
|  | params | param values for the next view
| getParameters() | get the parameter string which was transferred from the previous view
| cleanViewCache() | this function is available for portal app
while will remove all the cached view infor form the cache